## Sheet1
Eric Yanovich - January Checklist Mar. 1st 2006
Week | Day | Febuary Checklist
2006-02-01 | 1 | Continued using Etabs for model, but ran into sizing issues - Had to re-model in RAM
| 2 | Double checked wind/seismic spreadsheet | ü
3
2006-02-06 | 6 | Steel Frame Model was started in RAM | ü
| 7 | Getting bugs worked out in Ram model and incorporating concrete systems into design | ü
8
9
| 10 | Finishing up Steel Model | ü
2006-01-23 | 13 | Steel Frame Model was completed in RAM | ü
14
| 15 | Steel member sizes were found with Ram for gravity system and floor framing | ü
16
17
2006-01-30 | 20 | ensure that ram model has acurate sizes compared to hand checks | —
| 21 | replace lateral shear walls with braced or moment frame and compare systems | —
Notes:
So far I am pretty close the scheduled delievery articles, except for problems in computing steel sizes in ETABS. I was pushed back significantly since I had to remodel my building in Ram to quickly compute steel gravity floor system sizes. Currently I'm behind schedule by 2 weeks due the modeling problems, but will be getting the lateral system replacement finished soon and should be done with most CM (cost and constructibilbyt issues before the TOC is due. All in all I am slightly behind but I feel I can catch up quickly.