## Sheet1
THESIS PROGRESS SCHEDULE 2/9/08 |  | Alex Wyczalkowski
McKinstry Oregon Headquarters |  | Mechanical Option
Portland Oregon |  | Dr. Jelena Srebric
Progress
Week | Activities |  | 25% | 50% | 75% | 100%
2009-01-12 | Update Proposal and Breadth Proposal |  | × | × | × | ×
| Meet with Professor Srebric |  | × | × | × | ×
| Progress Schedule |  | × | × | × | ×
2009-01-19 | DOAS/Panel Research |  | × | × | × | ×
| Size Radiant Panels |  | × | × | x
Milestone: Jan 26 | Preliminary Research Done
2009-01-26 | Test Panels for Condensation |  | × | x | x | x
2009-02-02 | Lighting Breadth |  | x
Milestone: Feb 9 | Lighting Breadth complete
Radiant Panels Sized
2009-02-09 | Finish Sizing Radiant Panels
Resize AHU and Ductwork
2009-02-16 | Lighting Breadth
Coordinate Ceilings
Milestone: Feb 23 | Redesign Complete
2009-02-23 | Energy Model
2009-03-02 | Acoustics Breadth
2009-03-09 | SPRING BREAK
Milestone: March 16 | Substantial Completion of Research
2009-03-16 | Begin Report
Check Calculations
Optional Research on Combined Heat and Power
2009-03-23 | Begin Presentation Design
Optional Research on Combined Heat and Power
2009-03-30 | Work On Report
Work On Presentation
Optional Research on Combined Heat and Power
2009-04-06 | Finish Report
Finish Presentation
2009-04-13 | Presentation Week
2009-04-20 | ABET Evaluation
CPEP Update
NOTES: | Feb 9 Milestone NOT met.
I ran into some problems with the Radiant Panel sizing. I am not overly concerned at this point, because I front loaded my schedule. I hope to finish sizing the panels this week, as well as resizing the AHU and ductwork. The following week I will finish the Lighting Breadth and I will be right back on track.