## Slide 1
Fisk Corporate Headquarters
Houston, Texas
Penn State AE Senior Capstone Project
Stephen Blanchard – Construction Management Option
Advisor: Dr. John Messner

## Slide 2
Project Summary
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Project Location
Houston, Texas
Building Information
Office Size: 37,780 Sq. Feet
Pre-Fab Size: 16,380 Sq. Feet
2 Stories Above Grade
Structural Steel
Construction Logistics
Cost: $7,957,144
Duration: 11/21/11 – 10/5/12
Delivery: Design-Bid-Build
Contract Type: Lump Sum
Ownership Team Information
Fisk Electric Corp.
Tutor Perini Corp.
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 3
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Problem Identification
47 Week Construction Duration
Scheduling Gaps
Limited Activity Overlap (Finish to Start)
Background
Extensive General Conditions Implications
Fisk Electric Carried General Conditions
Includes Tutor Perini Staffing and Fees
General Conditions Overview
Total Cost: $1,122,906
14% of Construction Costs
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 4
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Original Structure Erection Schedule
Duration: 90 Days
All Activities on Critical Path
Relationships: Finish to Start (All Activities)
Separated Pours
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 5
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Re-Sequencing Process
1. Remove All Schedule Gaps
2. Re-Sequence Activities
3. Identify Potential Overlap
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 6
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Re-Sequencing Process
1. Remove All Schedule Gaps
2. Re-Sequence Activities
3. Identify Potential Overlap
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments
One
Month

## Slide 7
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Re-Sequencing Process
1. Remove All Schedule Gaps
2. Re-Sequence Activities
3. Identify Potential Overlap
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 8
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Re-Sequencing Process
1. Remove All Schedule Gaps
2. Re-Sequence Activities
3. Identify Potential Overlap
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 9
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Duration Results
Overall Schedule Reduced by 4 Weeks
No Activity Durations Were Altered
Phase Reductions
Office Sitework: 1 Week
Office Structure: 2 Weeks
Office Interiors: 1 Week
Non-Critical Path Phase Reductions
Fab-Shop Enclosure: 7 Weeks
Fab-Shop Interior: 2 Weeks
Landscape/Hardscape: 2 Weeks
Phase Duration Comparison
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 10
Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
General Conditions Savings Breakdown
General Conditions 5% Savings
Cost Implications
$50,698 Total GC Savings
Savings Type
$45,780 in Weekly Savings
$4,917 in Monthly Savings
Non-Quantifiable
Activity Duration Reductions
Crew Mobilizations
Crew Consistency
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 11
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Problem Identification
$1,223,400 Electrical Cost
Costly Distribution System
Redundant Components
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 12
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Problem Identification
$1,223,400 Electrical Cost
Costly Distribution System
Redundant Components
Original One-Line
Diagram
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 13
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Redesign Process
1. Eliminate Distribution Panel Redundancy
2. Streamline Step-Down Voltage System
3. Back-Feed Data Center Distribution System
Eliminate Distribution Panel Redundancy
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 14
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Redesign Process
1. Eliminate Distribution Panel Redundancy
2. Streamline Step-Down Voltage System
3. Back-Feed Data Center Distribution System
Streamline Step-Down Voltage System
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 15
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Redesign Process
1. Eliminate Distribution Panel Redundancy
2. Streamline Step-Down Voltage System
3. Back-Feed Data Center Distribution System
Back-Feed Data Center Distribution System
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 16
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 17
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Combined Distribution Panel
Redesign Results
1. Combined Distribution Panel
2. Single Step-Down Voltage Distribution System
3. Changes in Feeder Sizing and Distances
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 18
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Single Step-Down Voltage Distribution System
Redesign Results
1. Combined Distribution Panel
2. Single Step-Down Voltage Distribution System
3. Changes in Feeder Sizing and Distances
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 19
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Changes in Feeder Sizing and Distances
Redesign Results
1. Combined Distribution Panel
2. Single Step-Down Voltage Distribution System
3. Changes in Feeder Sizing and Distances
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 20
Electrical System Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Cost Impacts
Schedule Impacts
Constructability Concerns
David Rinehart
Ted Robertson
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 21
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Project LEED Facts
A/E Instructed to Design LEED Facility
35% Additional Area – 60% of Electric Bill
48 Points Available w/ No Design Changes
Did Not Apply for LEED Building Certification
No Construction LEED Practices Implemented
Business Case
Tax Incentives
1% Certified
2.5% Silver
Contractor Reputation
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 22
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Construction LEED Implementation Cost Summary
GBCI Fees
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 23
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Problem Identification
2 Points from LEED Silver
7/19 Optimize Energy Performance Credits
2% Energy Efficiency Increase = 1 LEED Credit
Goal – Improve Energy Efficiency by 4%
Currently No Window Shading System
Western/Eastern Facade
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 24
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Southeastern Corner Façade Rendering
Southwestern Corner Façade Rendering
Architectural Shade #1
6’ Overhang
Above Second Story Grazing
E, S, & W Facades
Material: Solid Black Aluminum Paneling
Supports: Steel Columns Buried in Ground
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 25
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Southwestern Corner Façade Rendering
Southeastern Corner Façade Rendering
Architectural Shade #2
6’ Overhang
Above Second Story Grazing
E, S, & W Facades
Material: White, Acrylic Translucent Glazing
Supports: Steel Columns Buried in Ground
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 26
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Southern Façade Rendering
Louver Detail
Architectural Shade #3
6’ Overhang
Above Second Story Grazing
E, S, & W Facades
Material: Louvered Metallic
Panes
Supports: Steel Columns Buried in Ground
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 27
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Total Annual Energy
  Left = Before Shading; Right = After Shading
CO2 Emissions
Peak Energy Demand
Eastern Façade Energy Summary
Total Annual Energy Savings
11.9 (kBtu/ft^2)
Peak Electric Demand Savings
1.6 (W/ft^2)
CO2 Emissions Reduction
5.5 (lbs/ft^2)
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 28
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Energy Summary
Average Energy Reduction
12%
Affected to Unaffected Ratio
1:2
12% * 1/3 = 4%
*Loading Higher in Solar Areas vs. Non-Solar
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 29
LEED Implementation
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
“Two Dimensions”
BIM to Implement Architectural Overhangs
Overhangs Designed in Revit
Easy to Communicate Technical Overhang Information to Team
Quicker Transition Between the Designs
4D Installation Sequence
Problem Background
Unusual Façade Installation
$20,000 in Back Chargers
Façade Already Modeled by Architect & Structural
$5,280 to Implement BIM Façade Detailing
Worker Tolerance Error
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 30
Final Recommendations
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Analysis #1: Project Sequencing
Cost Savings: $50,698
Schedule Savings: 4 Weeks
5% Reduction in Owner Carried General Conditions
Analysis #2: Electrical System Redesign
Cost Savings: $11,669
Schedule Savings: 4.5 Days
Fewer Components to Maintain & Service
No Additional Constructability Concerns
Analysis #3
Cost Incurred: $28,266
Gained LEED Building Certification
1% Reduction in State Property Tax
Improved Specialty Contractor Image
Architectural Overhangs Adopted
Gained LEED Silver
4% Minimum Improvement in Energy Efficiency
BIM Implementation to Ease Design Change
Savings Summary
Analysis #1
$50,698
Analysis #2
$11,669
Analysis #3
($28,266)
Total Savings
$34,101
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 31
Acknowledgements
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Industry
Special Thanks
Wayne McDonald
David Rinehart
Ted Robertson
Fisk Corporate Headquarters Project Team
PACE Industry Members
My Family and Friends
Academic
Dr. John Messner
Dr. Robert Leicht
Dr. Richard Mistrick
Professor Dodson
Professor Holland
Penn State AE Faculty
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 32
Questions?
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Analysis #1: Project Sequencing
Cost Savings: $50,698
Schedule Savings: 4 Weeks
5% Reduction in Owner Carried General Conditions
Analysis #2: Electrical System Redesign
Cost Savings: $11,669
Schedule Savings: 4.5 Days
Fewer Components to Maintain & Service
No Additional Constructability Concerns
Analysis #3
Cost Incurred: $28,266
Gained LEED Building Certification
1% Reduction in State Property Tax
Improved Specialty Contractor Image
Architectural Overhangs Adopted
Gained LEED Silver
4% Minimum Improvement in Energy Efficiency
BIM Implementation to Ease Design Change
Savings Summary
Analysis #1
$50,698
Analysis #2
$11,669
Analysis #3
($28,266)
Total Savings
$34,101
Project Summary
Analysis #1: Project Sequencing
Sequencing Process
Schedule Results
Cost Implications
Analysis #2: Electrical System Redesign
Electrical Redesign
Redesign Impacts
Analysis #3: Implementation of LEED
LEED Cost Analysis
Architectural Breadth
Energy Impacts
BIM Research
Final Recommendations
Acknowledgments

## Slide 33
Appendices – Project Sequencing
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Revised General Conditions Estimate
Original General Conditions Estimate

## Slide 34
Appendices – Electrical Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Panelboard DP
Panelboard H-1
Panelboard H-2

## Slide 35
Appendices – Electrical Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Panelboard L-1
Panelboard L-1B
Original Bill of Material

## Slide 36
Appendices – Electrical Redesign
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Original Bill of Material
Redesigned Bill of Material
Redesigned Bill of Material

## Slide 37
Appendices – LEED
Fisk Corporate Headquarters
Houston, Texas
Stephen Blanchard
Construction Management
Eastern Façade Energy Charts
Southern Façade Energy Charts
Western Façade Energy Charts