## Slide 1
Library In Metropolitan Washington, D.C.
Lowell Stine | Construction | Rob Leicht
Penn State Architectural Engineering Senior Capstone Project
Picture Provided by Multivista
1

## Slide 2
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Project Introduction
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Picture Provided by Multivista
2

## Slide 3
Project Introduction
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Key
Existing Buildings
Roads
Open Space
Sidewalks
Construction Site
Access Road
Building Footprint
Building Overhang
Site Trailers
Unloading Area
Future Apt. Site
Existing Building
10 Story
100’
Existing
Building
5 Story
60’
New Building
5 Story
85’
Building Name: Library in Metropolitan Washington, D.C.
Location: Metropolitan Washington, D.C. (Undisclosed)
Occupant: County Library & Non-profit Art Group
Function Types: A-3 (Assembly)
B (Business)
M (Mercantile)
Gross Area: 90,000 ft2
Number of Stories: Five Plus Basement
Project Delivery: Design-Bid-Build
Construction Dates: January 2013 – October 2014
Project Cost: $69.5 Million
Owner: Undisclosed County | Construction Manager: MBP | Civil Engineer: ADTEK
Architect: The Lukmire Partnership | Mechanical & Plumbing Engineer: Mendoza, Ribas, Farinas & Associates | Landscape Architect: Parker Rodriguez
Contractor: Costello Construction | Electrical Engineer: Mendoza, Ribas, Farinas & Associates | Interior Design: The Studio of Sandra Ragan
Structural Engineer: Columbia Engineering | IT/Security: Wright Engineering | Lighting Consultant: MCLA
Project Team
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
3

## Slide 4
Project Introduction
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
New Building
5 Story
85’
Systems
Architectural:
50’ Cantilever of 3rd thru 5th Floors
Exposed Structure in Library Space
Structure:
Concrete Caissons
Structural Steel
Composite Slabs
Building Enclosure:
53% Curtain Wall – UV Protection
Terra Cotta Panels
Architectural CMU’s
Mechanical:
IPEC (Integrated Packages Equipment Center)
Hydronic In-Slab Heating
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by Multivista
Picture Provided by http://www.systecon.com
Picture Courtesy of The Lukmire Partnership, Inc.
4

## Slide 5
Analysis Overview
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Early Involvement in Design Research Analysis
Caisson Rebar Cage Fabrication Analysis
Structural Sequencing Analysis
Structural Breadth
Mechanical Penthouse vs. IPEC Analysis
Acoustical Breadth
Design
Foundation
Structure
Building Systems
Programming
Design
Procurement
Construction
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Measurable Success
1) Minimize costs and schedule delays from change orders and rework
2) Minimize wasted material and labor costs and limit schedule delays
3) Shorten structural erection durations
4) Cost effectiveness and fewer constructability challenges
5

## Slide 6
Early Involvement in Design Research Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
6

## Slide 7
Early Involvement in Design Research Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
7
Goal
Considerations / Requirements
Specifics of this Project
Typical Problem Areas

## Slide 8
Early Involvement in Design Research Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Similar Topics |  | 
# | Criteria | Consistency
1 | Owner Buy-in | 5 of 5
2 | Cost Considerations | 5 of 5
3 | Scope Included | 5 of 5
4 | Relationship Outcomes | 4 of 5
5 | Quality & Project Flow | 4 of 5
6 | Schedule Considerations | 4 of 5
7 | Contract Considerations | 3 of 5
8 | Owner Involvement | 3 of 5
9 | Future of Early Involvement | 3 of 5
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
7
Goal
Considerations / Requirements
Specifics of this Project
Typical Problem Areas
Industry Member Interviews
Scopes
Benefits
Owner Buy-in
Future

## Slide 9
Early Involvement in Design Research Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Goal
Considerations / Requirements
Specifics of this Project
Typical Problem Areas
Industry Member Interviews
Scopes
Benefits
Owner Buy-in
Future
Mind Maps
Show Topics
Trace Patterns
Similar Topics |  | 
# | Criteria | Consistency
1 | Owner Buy-in | 5 of 5
2 | Cost Considerations | 5 of 5
3 | Scope Included | 5 of 5
4 | Relationship Outcomes | 4 of 5
5 | Quality & Project Flow | 4 of 5
6 | Schedule Considerations | 4 of 5
7 | Contract Considerations | 3 of 5
8 | Owner Involvement | 3 of 5
9 | Future of Early Involvement | 3 of 5
Mind Maps
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
7

## Slide 10
Early Involvement in Design Research Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Overall Conclusions
Smooth Transition Between Phases
Early Cost Influence
Programming
Design
Procurement
Construction
Ability to Influence Costs
Project Duration
Conception
High
Low
Completion
Programming
Design
Procurement
Construction
Close-out
Influence of Cost Curve
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Process Flow
8

## Slide 11
Early Involvement in Design Research Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
Earlier Involvement is Beneficial
Less Change Orders
Cost Savings
Funding Issues
Scope Selection (Project Specific)
Rating Scale |  |  |  | 
 | Owner | CM | Contractor | Design Team
Funding | X | - | - | -
Resources Available |  |  |  | 
Experience |  |  | X | 
Scope Inclusion Areas |  |  |  |  |  | 
Scopes | Program | Conceptual | Schematic Design | Design Development | Construction Documents | Construction
Contractor | Start-up | Scope Selection & Sign Contract | Sub Selection & Design Input | Sub Selection & Design Input | Design Input & Long Lead Items | Management
MEP | - | Planning, Questions & Sign Contract | Consult w/ Subs | Design Input | Design Input & Long Lead Items | Procurement
Structural | - | - | - | Consult w/ Subs, Design Input & Sign Contract | Design Input & Long Lead Items | Procurement
Curtain Wall | - | - | Consult w/ Subs & Sign Contract | Design Input | Design Input & Long Lead Items | Procurement
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
9

## Slide 12
Caisson Rebar Cage Fabrication
Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
10

## Slide 13
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Goal
Determine Appropriate Fabrication Method
Cost Savings
Scheduled Reduction
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by Multivista
11

## Slide 14
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Goal
Determine Appropriate Fabrication Method
Cost Savings
Scheduled Reduction
Background
9 Caisson Types (48 Total)
Prefab to Planned Length
Planned Lengths Incorrect
15 Day Delay
Caisson Types |  |  |  |  |  | 
Type | Vertical Rebar # | Qty. of Vertical Rebar | Tie # | # of Ties per LF | Weight of Vertical Rebar (lb/LF) | Weight of Ties (lb/LF)
1a | 9 | 8 | 4 | 1 | 27 | 6
1b | 9 | 6 | 4 | 1 | 20 | 6
2a | 11 | 8 | 4 | 1 | 43 | 9
2b | 11 | 12 | 4 | 1 | 64 | 11
2c | 11 | 16 | 4 | 1 | 85 | 13
2d | 11 | 24 | 4 | 1 | 128 | 15
2e | 11 | 28 | 5 | 1 | 149 | 21
2f | 11 | 16 | 4 | 2 | 85 | 27
2g | 11 | 28 | 5 | 2 | 149 | 41
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by Multivista
11

## Slide 15
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Goal
Determine Appropriate Fabrication Method
Cost Savings
Scheduled Reduction
Background
9 Caisson Types (48 Total)
Prefab to Planned Length
Planned Lengths Incorrect
15 Day Delay
Fabrication Methods
100% Planned
Planed + 10%
80% of Planned
10’ Sections
15’ Sections
Caisson Types |  |  |  |  |  | 
Type | Vertical Rebar # | Qty. of Vertical Rebar | Tie # | # of Ties per LF | Weight of Vertical Rebar (lb/LF) | Weight of Ties (lb/LF)
1a | 9 | 8 | 4 | 1 | 27 | 6
1b | 9 | 6 | 4 | 1 | 20 | 6
2a | 11 | 8 | 4 | 1 | 43 | 9
2b | 11 | 12 | 4 | 1 | 64 | 11
2c | 11 | 16 | 4 | 1 | 85 | 13
2d | 11 | 24 | 4 | 1 | 128 | 15
2e | 11 | 28 | 5 | 1 | 149 | 21
2f | 11 | 16 | 4 | 2 | 85 | 27
2g | 11 | 28 | 5 | 2 | 149 | 41
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by Multivista
11

## Slide 16
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
30’ Max Cage Length
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by www.rebarsuply.net
12

## Slide 17
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
30’ Max Cage Length
Truck Crane Installation
Concrete Pump Placement
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by www.rebarsuply.net
Picture Provided by Multivista
12

## Slide 18
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
30’ Max Cage Length
Truck Crane Installation
Concrete Pump Placement
High Splice Costs
Cut-off Higher Productivity
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by http://news.thomasnet.com/
Picture Provided by www.rebarsuply.net
Picture Provided by Multivista
12

## Slide 19
Caisson Rebar Cage Fabrication Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
30’ Max Cage Length
Truck Crane Installation
Concrete Pump Placement
High Splice Costs
Cut-off Higher Productivity
Use 100% Prefabricated Method
Accept Unknowns
Prefabrication Option Comparison |  |  |  |  | 
Caisson Types | Base Line | Over 10% Prefab Estimation | Prefab 80% of Estimation | 10’ Length Sections | 15’ Length Sections
1a | $ 1,207.13 | $ 2,018.26 | $ 580.70 | $ 2,545.31 | $ 1, 040.01
1b | $ 1,756.59 | $ 2,059.49 | $ 993.63 | $ 579.61 | $ 285.71
2a | $ 2,313.82 | $ 2,827.37 | $ 1,856.53 | $ 3,661.62 | $ 1,512.15
2b | $ 1,845.69 | $ 2,300.02 | $ 937.03 | $ 2,177.57 | $ 260.10
2c | $ - | $ - | $ - | $ 2,022.40 | $ 1,011.20
2d | $ 1,516.80 | $ - | $ 1,516.80 | $ 3,033.60 | $ 1,516.80
2e | $ 12,484.19 | $12,139.79 | $ 13,377.24 | $ 33,762.24 | $ 15,289.27
2f | $ - | $ 243.22 | $ 3,024.00 | $ 3,725.88 | $ -
2g | $ 1,827.72 | $ 2,183.29 | $ 1,116.59 | $ - | $ 808.19
Grand Totals | $ 22,951.94 | $ 32,329.00 | $ 23,402.52 | $ 51,508.23 | $ 21,723.43
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by http://news.thomasnet.com/
Picture Provided by www.rebarsuply.net
Picture Provided by Multivista
12

## Slide 20
Structural Sequencing
Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
13

## Slide 21
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Goal
Reevaluate Structural Sequence
Save Erection Costs
Shorten Erection Schedule
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
14

## Slide 22
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Goal
Reevaluate Structural Sequence
Save Erection Costs
Shorten Erection Schedule
Background Information
Current Erection
Complex Erection Sequence
5 Week Delay
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
14

## Slide 23
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
15
Shoring Sequence
Linear

## Slide 24
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Shoring Sequence
Linear
4-D Comparisons
Slabs After Shoring
Hanger Resizing?
1
4
3
2
5
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
15

## Slide 25
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
16
Complexity of Erection
Complex structure
Inconsistent erection sequence

## Slide 26
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
16
Complexity of Erection
Complex structure
Inconsistent erection sequence
Site
Very urban site
Shoring will occupy large area
Tight delivery scheduling

## Slide 27
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
16
Complexity of Erection
Complex structure
Inconsistent erection sequence
Site
Very urban site
Shoring will occupy large area
Tight delivery scheduling
Safety
High priority
Dangerous welding locations
OSHA compliance
Picture Provided by Multivista

## Slide 28
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Complexity of Erection
Complex structure
Inconsistent erection sequence
Site
Very urban site
Shoring will occupy large area
Tight delivery scheduling
Safety
High priority
Dangerous welding locations
OSHA compliance
Trade Integration
Delay of MEP rough-in start-up
MEP Rough-in Start Dates |  | 
Description | Top-Down Option | Shoring Option
MEP Rough-in Start | 10/23/13 | 11/14/13
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
16
Picture Provided by Multivista

## Slide 29
Structural Breadth - Shoring Design
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
17
Required Shoring Load
Dead Loads
Live Loads
Pu= 291 psf

## Slide 30
Structural Breadth - Shoring Design
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
17
Required Shoring Load
Dead Loads
Live Loads
Pu= 291 psf
Picking Shoring System
Mabey’s Mass Series
Shoring Towers
Picture Provided by Mabey Inc.

## Slide 31
Structural Breadth - Shoring Design
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
17
Required Shoring Load
Dead Loads
Live Loads
Pu= 291 psf
Picking Shoring System
Mabey’s Mass Series
Shoring Towers
Finalize Shoring Design
Mass 25 - 100 kips
Space at 20’x18’
(16) 5’x5’ & (2) 5’x10’
Picture Provided by Mabey Inc.

## Slide 32
Structural Breadth - Shoring Design
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Required Shoring Load
Dead Loads
Live Loads
Pu= 291 psf
Picking Shoring System
Mabey’s Mass Series
Shoring Towers
Finalize Shoring Design
Mass 25 - 100 kips
Space at 20’x18’
(16) 5’x5’ & (2) 5’x10’
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
17

## Slide 33
Structural Sequencing Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
3 Week Schedule Savings (with shoring install)
$30,000 Savings
Better Productivity (Specific Zones)
Recommend the Shoring Sequence
Shoring Cost Break Down |  | 
Description | Per Tower | Total
Minimum First 4 Weeks | $1357 | $24,430
Every Week After for 4 Weeks | $828 | $14,900
Tax (6%) | $131 | $2,360
Total | $2,316 | $41,690
Cost Comparisons | 
Description | Per Tower
General Condition Savings | $72,000
Shoring Costs | $41,690
Total Estimated Costs Savings | $30,000
Zone Delays
Structure Duration Comparisons |  |  | 
Description | Planned | Top-Down Option | Shoring Option
Steel Erection Start | 6/25/13 | 7/4/13 | 7/4/13
Structure Complete Milestone | 1/1/14 | 3/7/14 | 2/13/14
Total Duration (weeks) | 28 | 33 | 30
IPEC vs. Mechanical Penthouse |  | 
Criteria & Categories | Top-Down | Shoring
Constructability | x | 
Schedule | x | 
Cost |  | 
Site |  | x
Safety | x | 
Other Trades | x | 
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
18

## Slide 34
Mechanical Penthouse vs. IPEC
Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
19

## Slide 35
Mechanical Penthouse vs. IPEC Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
20
Goals
IPEC & Penthouse Differences
How to Chose Which to Use
Gain Knowledge of Each

## Slide 36
Mechanical Penthouse vs. IPEC Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Integrated Packaged Equipment Center (IPEC)
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Provided by MBP (Construction Documents Courtesy of MBP)
20
Goals
IPEC & Penthouse Differences
How to Chose Which to Use
Gain Knowledge of Each
IPEC
Prefabricated Equipment Module
4’ CMU Base Wall
One Supplier

## Slide 37
Mechanical Penthouse vs. IPEC Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Integrated Packaged Equipment Center (IPEC)
Mechanical Penthouse
Goals
IPEC & Penthouse Differences
How to Chose Which to Use
Gain Knowledge of Each
IPEC
Prefabricated Equipment Module
4’ CMU Base Wall
One Supplier
Mechanical Penthouse
Site Constructed
On Concrete Structural Roof
Multiple Different Suppliers
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by http://www.jetsongreen.com/
20

## Slide 38
Acoustical Breadth
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Kids Section
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Provided by MBP (Construction Documents Courtesy of MBP)
21
          Acoustical Impacts of IPEC and Penthouse
          Library Spaces
          Outdoor Environment
          Differences
          Similar Acoustical Properties
          Over Estimates

## Slide 39
Acoustical Breadth
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
          Acoustical Impacts of IPEC and Penthouse
          Library Spaces
          Outdoor Environment
          Differences
          Similar Acoustical Properties
          Over Estimates
          Recommendations
          IPEC Would Be More Desirable
Kids Section
Noise Levels |  | 
 | Limit | Actual
Conference Room | 35 dB | 37 dB
Property Line | 55 dB | 57 dB
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
21
Provided by MBP (Construction Documents Courtesy of MBP)

## Slide 40
Mechanical Penthouse Vs. IPEC Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Results
1 Week On Site vs. 10.5 Weeks On Site
Potential $1 Million Savings
Flexible Design
Penthouse
Design-Build Package
IPEC vs. Mechanical Penthouse Costs |  |  | 
System | Equipment | Enclosure/ Structure | Total
IPEC | $5,800,000 | $50,000 | $5,850,000
Penthouse | $4,880,000 | $100,000 | $4,880,000
IPEC vs. Mechanical Penthouse Schedule |  | 
System | Lead Time | Site Install Time
IPEC | 1 Long Lead Item (Months) | 1 Week
Penthouse | Multiple Shorter Lead Times (Weeks) | 10.5 Weeks
IPEC vs. Mechanical Penthouse |  | 
Criteria & Categories | IPEC | Penthouse
Acoustical |  | 
Maintenance | x | 
Flexibility in Design | x | 
Responsibility |  | 
Constructability |  | 
Costs | x | 
Schedule |  | x
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
22

## Slide 41
Conclusions
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Design (Early Involvement)
Foundation (100% Prefabrication Cage Length)
Structure (Shoring Sequence)
Building Systems (Mechanical Penthouse)
Early Involvement
Undetermined Cost Savings
Undetermined Schedule Savings
100% Prefabrication Cage Length
$0.00 Savings
Account for Caissons in Schedule
Shoring Sequence
$30,000 Savings
3 Week Schedule Savings
Mechanical Penthouse
Possible $1 Million Savings
Additional 9.5 Week Mechanical Schedule
Programming
Design
Procurement
Construction
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
23

## Slide 42
Acknowledgments
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
Questions?
Academic
Michelle Vigeant
Moses Ling
Dr. Robert Leicht
Kevin Parfitt
Ray Sowers
Special Thanks
Library’s Owner
PACE Industry Members
Matt Strevig
Friends and Family
Outline
  Project Introduction
  Early Involvement
  Caisson Rebar Cage Prefab Structural Sequencing
  Structural Breadth
  Mechanical Room
  Acoustical Breadth
  Summary of Conclusions
  Acknowledgments
Picture Provided by Multivista
24

## Slide 43
Structural Analysis
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
25
Shoring Sequence Schedule
Current Structural Schedule
General Conditions Costs

## Slide 44
Structural Breadth - Shoring Load Calcs.
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
26
Dead Load Calculations
Live Load & Factored Loads
Live Load Assumptions
Started with 50 psf
Four floors is 200 psf
In live load reduction total is 129 psf
Factored live load would then be 206 psf
(This would be an acceptable live load on four floors of only structure)

## Slide 45
Acoustical Breadth Calculations
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
27
Zone 2 Acoustics

## Slide 46
Acoustical Breadth Calculations
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
28
Conference Room Acoustics

## Slide 47
Penthouse Costs
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
29
Equipment
Enclosure

## Slide 48
Penthouse Durations
Lowell Stine | Construction
Library In Metropolitan Washington, D.C.
30
Equipment
Enclosure