## Slide 1
Northeast Hospital Expansion
Penn State AE Senior Thesis Project
Joshua Miller | Construction Management Option
Faculty Advisor | Craig Dubler
Courtesy of Smith Group JJR

## Slide 2
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Introduction
Northeast Hospital Expansion
123 Medical Lane, USA
Project Background
Key
Elect. Main
Water Main
Const. Parking
Ambulance
Bay/Access
Const. Access
Res. Zoning
New Const.
Building Information
  234,000 SF
  10 Stories
  120 Private Patient Rooms
  $230 Million ($121 million for new patient tower)
Project Schedule
  Start Date: January 2013
  Completion Date: September 2015
  Total Duration: 973 work days
Project Manager
  Whiting-Turner
  Construction Manager at Risk
  Guaranteed Maximum Price

## Slide 3
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Introduction
Northeast Hospital Expansion
123 Medical Lane, USA
Analysis Overview
Analysis 1: Implementing an Integrated Project Delivery
Observing how similar projects in the US are implementing IPD strategies that could have been used to create a more efficient project team and suggesting how apply these methods.
Analysis 2: Patient Room Re-Design for Shared Wet Wall
Re-evaluating the plumbing design for the private patient rooms to create a more efficient design that potentially saves on labor time and material costs.
Mechanical Breadth: Re-sizing the sanitary, vent, and the cold and hot water supplies
Analysis 3: SIPS Utilization for Patient Floors
Applying short interval production scheduling to the MEP installations and finishes on the private patient floors for an accelerated schedule and more balanced workflow.
Analysis 4: Preassembled Steel Connection Bridge
Identifying sections of the bridge connecting the existing hospital to the patient tower addition for preassembly in order to create a safer work environment and reduce the time spent on steel erection.
Structural Breadth: Verifying the preassembled sections can be picked by the crane and designating pick points .
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 4
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Northeast Hospital Expansion
123 Medical Lane, USA
Analysis 1: Implementing an Integrated Project Delivery
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 5
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Current Delivery Method
Owner
Smith Group JJR
Architect
Whiting -Turner
Construction Manager at Risk
Southland Industries
Mech/Plumbing Contractor
Dynalectric
Electrical Contractor
Other Subcontractors
McMullan & Associates, Inc.
Structural Engineer
Leach Wallace Associates, Inc.
MEP/FP Engineering
Syska Hennessey Group
MEP/FP Engineering
Loiederman Soltesz Associates
Civil Engineers
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Northeast Hospital Expansion |  |  |  |  |  |  | 
9 miles
16.4 miles
13 miles
24 miles
McMullan & Associates, Inc.
Syska Hennessey Group
Leach Wallace Associates, Inc.
Smith Group JJR
Loiederman Soltesz Associates
26 miles
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 6
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Case Studies of Similar Projects Using IPD
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Northeast Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children's Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children’s Hospital
Courtesy of Christer Inc.
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 7
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Case Studies of Similar Projects Using IPD
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Northeast Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children's Hospital Expansion |  |  |  |  |  |  | 
St. Clare Health Center |  |  |  |  |  |  | 
St. Clare Health Center
Courtesy of Kwame Building Group.
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 8
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Case Studies of Similar Projects Using IPD
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Northeast Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children's Hospital Expansion |  |  |  |  |  |  | 
St. Clare Health Center |  |  |  |  |  |  | 
Encircle Health's Ambulatory Care Center |  |  |  |  |  |  | 
Encircle Health’s Ambulatory Care Center
Courtesy of HGA
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 9
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Case Studies of Similar Projects Using IPD
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Northeast Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children's Hospital Expansion |  |  |  |  |  |  | 
St. Clare Health Center |  |  |  |  |  |  | 
Encircle Health's Ambulatory Care Center |  |  |  |  |  |  | 
Cathedral Hill Hospital |  |  |  |  |  |  | 
Cathedral Hill Hospital
Courtesy of Smith Group
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 10
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Case Studies of Similar Projects Using IPD
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Northeast Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children's Hospital Expansion |  |  |  |  |  |  | 
St. Clare Health Center |  |  |  |  |  |  | 
Encircle Health's Ambulatory Care Center |  |  |  |  |  |  | 
Cathedral Hill Hospital |  |  |  |  |  |  | 
Health Sciences Facility III |  |  |  |  |  |  | 
Health Sciences Facility III
Courtesy of the University of Maryland
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 11
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 1: Implementing an Integrated Project Delivery
Northeast Hospital Expansion
123 Medical Lane, USA
Suggested Methods for Implementation
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Proposed Northeast Hospital Expansion |  |  |  |  |  |  | 
Northeast Hospital Expansion |  |  |  |  |  |  | 
Cardinal Glennon Children's Hospital Expansion |  |  |  |  |  |  | 
St. Clare Health Center |  |  |  |  |  |  | 
Encircle Health's Ambulatory Care Center |  |  |  |  |  |  | 
Cathedral Hill Hospital |  |  |  |  |  |  | 
Health Sciences Facility III |  |  |  |  |  |  | 
Smith Group JJR
Architect
Whiting -Turner
CM at Risk
Southland Industries
Mech/Plumb
Dynalectric
Electrical
Other Subcontractors
McMullan & Associates, Inc.
Struct. Eng.
Leach Wallace Associates, Inc.
MEP/FP Eng.
Syska Hennessey Group
MEP/FP Eng.
Loiederman Soltesz Associates
Civil Eng.
Owner
Negotiated Space for Part-Time Co-Location
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 12
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Northeast Hospital Expansion
123 Medical Lane, USA
Analysis 2: Patient Room Re-Design for Shared Wet Wall
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 13
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 2: Patient Room Re-Design for Shared Wet Wall
Northeast Hospital Expansion
123 Medical Lane, USA
Existing/Proposed Patient Room Layout
Existing Patient Room Layout
Proposed Patient Room Layout
ADA 2010 Considerations
Change of Water Closet and Carrier
Josam Series 12694
Patient Quality of Care
  Pittsburgh’s UPMC Study on Patient Room Size
    Patient Room Area = 220SF is Optimum
    Reduces Patient falls
    Decrease in readmission rate
  Proposed patient room area = 228SF
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 14
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 2: Patient Room Re-Design for Shared Wet Wall
Northeast Hospital Expansion
123 Medical Lane, USA
Mechanical Breadth: Piping Re-Sizing
Sanitary and Vent Piping Schematic
Table 710.1 (2): Sanitary Drainage Sizing
Table 916.1: Vent Size and Developed Length
*Tables referenced from the 2009 International Plumbing Code
Number of Drainage Fixture Units (dfu)
Fixture Type | Dfu Value
Lavatory | 1
Shower (Flow Rate < 5.7 gpm) | 2
Water Closet, public (1.6 gpf) | 4
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 15
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 2: Patient Room Re-Design for Shared Wet Wall
Northeast Hospital Expansion
123 Medical Lane, USA
Mechanical Breadth: Piping Re-Sizing
CW and HW Supply Piping Schematic
Load Value, Water Supply Fixture Units (wsfu)
Fixture Type | Wsfu Values | 
 | Cold | Hot
Lavatory (Public, Faucet) | 1.5 | 1.5
Shower (Public, Mixing Valve) | 3.0 | 3.0
Water Closet (Public, Flush Valve) | 10.0 | -
*Tables referenced from the 2009 International Plumbing Code
8 ft/sec Velocity
Portion of Branch | Wsfu | Gpm
 | 3.0 | 6.5
 | 1.5 | 5.0
Converting from wsfu to Gallon per minute (gpm)
5/8”
1/2”
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 16
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 2: Patient Room Re-Design for Shared Wet Wall
Northeast Hospital Expansion
123 Medical Lane, USA
Cost and Schedule Impact
System | Existing Design | Proposed Design | Difference | % Change
CW & HW Supply | $1,508.55 | $1,580.26 | ($71.71) | 105%
Sanitary | $10,889.13 | $5,437.89 | $5,451.24 | 50%
Vent | $1,139.27 | $930.69 | $208.58 | 82%
Insulation | $1,353.70 | $794.88 | $558.82 | 59%
Total | $14,890.65 | $7,948.84 | $6,941.81 | 53%
System | Existing Design | Proposed Design | Difference | % Change
CW & HW Supply | $2,042.36 | $1,367.62 | $674.74 | 67%
Sanitary | $5,582.68 | $2,440.21 | $3,142.47 | 44%
Vent | $1,166.72 | $965.83 | $200.89 | 83%
Insulation | $ 879.18 | $477.37 | $401.81 | 54%
Total | $9,670.94 | $4,773.66 | $4,897.28 | 49%
Material Cost Comparison Per Patient Room Pair
Labor Costs Comparison Per Patient Room Pair
System | Existing Design | Proposed Design | Difference | % Change
CW & HW Supply | 35.6 | 23.7 | 11.9 | 67%
Sanitary | 108.5 | 47.5 | 61 | 44%
Vent | 27 | 22.7 | 4.3 | 84%
Insulation | 17.1 | 9.4 | 7.7 | 55%
Total | 188.2 | 94 | 94.2 | 50%
Labor Hour Comparison Per Patient Room Pair
Design | Schedule Acceleration | Material Costs | Labor Costs | Total Cost
Existing | - | $670,079.25 | $435,192.30 | $1,105,271.55
Proposed | 93 days | $357,697.80 | $214,814.70 | $572,512.50
Total Schedule & Cost Reduction Summary
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements
Savings
$532,759

## Slide 17
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Northeast Hospital Expansion
123 Medical Lane, USA
Analysis 3: SIPS Utilization for Patient Floors
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 18
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 3: SIPS Utilization for Patient Floors
Northeast Hospital Expansion
123 Medical Lane, USA
Original Crew Sizes & Proposed Work Zones
6
5
4
3
2
1
0
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 19
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 3: SIPS Utilization for Patient Floors
Northeast Hospital Expansion
123 Medical Lane, USA
Workflow Balancing
Each Activity has 1 week to complete 1 zone
Crews to complete 900 SF per day
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 20
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 3: SIPS Utilization for Patient Floors
Northeast Hospital Expansion
123 Medical Lane, USA
Workflow Balancing
(Proposed SF/Day)
(Original SF/Day)
X
(Original Crew Size) = (Proposed Crew Size)
(Proposed Crew Size)
X
(Hourly Cost/Worker)
X
8 Hrs = (Total Cost/Day)
(Total Cost/Day)
X
5 Zones/Floor = (Total Cost/Floor)
X
5 Days/Zone
(Total Cost/Floor)
X
3 Patient Floors = (Total Project Cost/Activity)
Σ(Total Project Cost/Activity) = Total Project Cost
6
5
4
3
2
1
0
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 21
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 3: SIPS Utilization for Patient Floors
Northeast Hospital Expansion
123 Medical Lane, USA
Workflow Balancing
(Proposed SF/Day)
(Original SF/Day)
X
(Original Crew Size) = (Proposed Crew Size)
(Proposed Crew Size)
X
(Hourly Cost/Worker)
X
8 Hrs = (Total Cost/Day)
(Total Cost/Day)
X
5 Zones/Floor = (Total Cost/Floor)
X
5 Days/Zone
(Total Cost/Floor)
X
3 Patient Floors = (Total Project Cost/Activity)
Σ(Total Project Cost/Activity) = Total Project Cost
6
5
4
3
2
1
0
Chart: 
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 22
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Analysis 3: SIPS Utilization for Patient Floors
Northeast Hospital Expansion
123 Medical Lane, USA
Cost and Schedule Impact
Schedule Type | Original | SIPS
Labor Cost | $2,992,027.20 | $2,979,930.00
Start Date | 3/5/14 | 3/5/14
End Date | 7/22/15 | 3/18/15
Duration (days) | 504 | 378
Labor Savings: $12,097.20
Schedule Acceleration:126 days (18 weeks)
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 23
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Conclusions & Recommendations
Northeast Hospital Expansion
123 Medical Lane, USA
Analysis 1: Implementing an Integrated Project Delivery
Analysis 2: Patient Room Re-Design for Shared Wet Wall
Analysis 3: SIPS Utilization for Patient Floors
Project | Multi-Party contract | Liability Waivers | Risk/ Reward Pool | Integrated Team Structure | Early Involvement of Key Players | Co-location | Network Sharing
Proposed Northeast Hospital Expansion |  |  |  |  |  |  | 
Design | Schedule Acceleration | Material Costs | Labor Costs | Total Cost
Existing | - | $670,079.25 | $435,192.30 | $1,105,271.55
Proposed | 93 days | $357,697.80 | $214,814.70 | $572,512.50
Schedule Type | Original | SIPS
Labor Cost | $2,992,027.20 | $2,979,930.00
Start Date | 3/5/14 | 3/5/14
End Date | 7/22/15 | 3/18/15
Duration (days) | 504 | 378
Savings
$12,097.20
126 days (18 weeks)
Savings
$532,759.05
✔
✔
✔
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements
General Conditions: $13,027,770 Total
973 total original work days
$13,389.28 per day

## Slide 24
AE Senior Thesis Project
Joshua Miller | Construction Management Option
Acknowledgements
Northeast Hospital Expansion
123 Medical Lane, USA
Special Thanks To:
John Ovelman – Whiting-Turner
Chris Brooks – Southland Industries
Raj Vora – Southland Industries
John Carbonneau – Southland Industries
Adam Davis – Penn State Office of Physical Plant
Mark Bittner – CBRE Healthcare
Jake Hughes – CBRE Healthcare
PACE Industry Members
My Friends, Family, and A-7
Academic:
Penn State Architectural Engineering Faculty
Dr. Craig Dubler – Faculty Advisor
Industry Acknowledgements:
Whiting-Turner
Southland Industries
CBRE Healthcare
I. Introduction
Project Background
Analysis Overview
II. Analysis 1: Implementing an Integrated Project Delivery
Current Delivery Method
Case Studies of Similar Projects Using IPD
Suggested Methods for Implementation
III. Analysis 2: Patient Room Re-Design for Shared Wet Wall
Existing/Proposed Patient Room Layout
Mechanical Breadth: Piping Re-Sizing
Cost and Schedule Impact
IV. Analysis 3: SIPS Utilization for Patient Floors
Original Crew Sizes & Proposed Work Zones
Workflow Balancing
Cost and Schedule Impact
V. Conclusions & Recommendations
VI. Acknowledgements

## Slide 25
Northeast Hospital Expansion
Thank you
Courtesy of Smith Group JJR
Questions?
Questions?