## Slide 2
Building Name Health Sciences Facility III Building Location Baltimore, MD Size 435,000 GSF
Number of Stories 11 above grade, 2 below Construction Date July 2013-September 2017 Construction Cost $206 Million Delivery Method CM at Risk
Project Team

## Slide 3
System | Amount
Demolition/Excavation | $7,616,000
Structure | $21,297,000
Envelope | $34,726,000
Mechanical/Plumbing | $62,903,000
Electrical | $32,357,000
Fire Protection | $1,965,000
Sitework | $2,672,800
Other | $42,956,200
General Conditions | $10,130,300
Total | $ 206,493,000
|Critical Path
|Site Logistics
Construction Cost

## Slide 4
Shoring | $1,480,000
Dewatering Issues | $650,000
New Total | $2,130,000
.712 miles
Analysis 1 | Shoring System
|Pile and Lagging

## Slide 5
Soil Property | Amt | Unit
Water Table | 20 | ft
Angle of Friction,  | 35 | Degrees ()
Moist Unit Weight,  | 125 | pcf
Sat Unit Weight, SAT | 145 | pcf
Construction surcharge, q | 250 | psf
Allowable bearing, qa | 5000 | psi
Soil Type | SM | --
Assumed Values
Calculated Values
Property | Amt | Unit
’=SAT -w | 82.6 | pcf
ka | .271 | 
kp | 3.69 | 

## Slide 6
Soil Property | Amt | Unit
Water Table | 20 | ft
Angle of Friction,  | 35 | Degrees ()
Moist Unit Weight,  | 125 | pcf
Sat Unit Weight, SAT | 145 | pcf
Construction surcharge, q | 250 | psf
Allowable bearing, qa | 5000 | psi
Soil Type | SM | --
Assumed Values
Calculated Values
P1= 1.355 k
P2= 6.775 k
P3= 8.943 k
P4=6.105 k
P5= 5.501 k
L3= 6.24 ft
Property | Amt | Unit
’=SAT -w | 82.6 | pcf
ka | .271 | 
kp | 3.69 | 

## Slide 7
Without Tiebacks
With Tiebacks
P1= 1.355 k
P2= 6.775 k
P3= 8.943 k
P4=6.105 k
P5= 5.501 k
L3= 6.24 ft
H= 24.4 ft
Total height= 62.64 ft
H= 5.5 ft
Total height= 44 ft
Tieback Force= 24k/ft
Shear and Moment
Mu=239ft k
Vu= 23.3 k
Soil Property | Amt | Unit
Water Table | 20 | ft
Angle of Friction,  | 35 | Degrees ()
Moist Unit Weight,  | 125 | pcf
Sat Unit Weight, SAT | 145 | pcf
Construction surcharge, q | 250 | psf
Allowable bearing, qa | 5000 | psi
Soil Type | SM | --
Assumed Values
Calculated Values
Property | Amt | Unit
’=SAT -w | 82.6 | pcf
ka | .271 | 
kp | 3.69 | 

## Slide 8
|Sheet Piles

## Slide 9
|Sheet Piles
|Slurry Wall

## Slide 10
Comparison Matrix
|Schedule
Shoring System | Price
Pile and Lagging | $2,130,000
Sheet Piles | $1,640,000
Slurry Wall | $3,029,810
|Cost
114 Days
90 Days
363 Days
|Recommendations
 | Pile and Lagging | Sheet Piles | Slurry Wall
Availability | ✔ | ✔ | ✔
Constructability |  | ✔ | 
Cost | ✔ | ✔ | 
Schedule | ✔ | ✔ | 
Sheet Piles Recommended ✔

## Slide 11
Analysis 2 | Motivation
Question: What are the drivers of motivation and how does that correlate with team performance?
?
Audience: Construction Managers
Method: Literature review and industry survey

## Slide 12
Survey Results
A respectable leader | Negative consequences
Formal recognition | Team reputation
Promotional opportunities | Negative feedback
Time off | An unmotivated team leader
A challenging project | The team
Money | When believe in the cause
A complex project | 
Not at All | Very Little | Somewhat | Significantly | Very Significantly
|Drivers of Motivation

## Slide 13
Survey Results
A respectable leader | Negative consequences
Formal recognition | Team reputation
Promotional opportunities | Negative feedback
Time off | An unmotivated team leader
A challenging project | The team
Money | When believe in the cause
A complex project | 
Not at All | Very Little | Somewhat | Significantly | Very Significantly
Driver | % Significant | Driver | % Insignificant
Believe in Cause | 100 | Unmotivated Team Member | 60
Respectable Leader | 97 | Negative Consequences | 43
A Challenging Project | 83 | Negative Feedback | 27
Team reputation | 80 | Time Off | 20
Assuming Leadership Position | 77 | Formal Recognition | 7
A Complex Project | 73 | Promotional Opportunities | 7
The Team | 63 | Team Reputation | 7
Promotional Opportunities | 60 | Money | 3
Money | 57 | A Complex Project | 3
Time Off | 53 | The Team | 3
Formal Recognition | 50 | Respectable Leader | 0
Negative Consequences | 37 | A Challenging Project | 0
Negative Feedback | 27 | Assuming Leadership Position | 0
Unmotivated Team Member | 10 | Believe in Cause | 0
|Drivers of Motivation

## Slide 14
|Negative Correlation
Survey Results
Driver #1 | Driver #2 | Degree of Correlation
A complex project | A challenging project | .70
When believe in the cause | The team | .58
The team | Motivated leader influences team performance | .54
Formal recognition | Promotional opportunities | .51
Promotional opportunities | Time off | .45
Driver #1 | Driver #2 | Degree of Correlation
Money | Degree motivation related to team performance | -.44
A complex project | Motivated leader influences team performance | -.43
Money | Assuming a leadership position | -.40
A complex project | Unmotivated leader influences team performance | -.39
Money | Motivated leaders influences team performance | -.38
|Positive Correlation

## Slide 15
Survey Results
|Age Correlation
Chart: 
| A respectable leader | Formal recognition | Promotional Opportunities | Time off | A challenging project | Money | A complex project | Negative consequences | Team reputation | Negative feedback | Unmotivated team member | Assuming a leadership position | When believe in the cause | The team
18-24 | 9.2857 | 5.7143 | 7.5 | 7.5 | 8.5714 | 6.0714 | 7.1429 | 5.7143 | 8.2143 | 4.2429 | 2.8857 | 7.5143 | 9.6429 | 7.8571
25-34 | 9.1667 | 7.5 | 7.0833 | 6.25 | 7.9167 | 8.3333 | 6.9833 | 4.1667 | 7.0833 | 5.4167 | 1.25 | 7.0833 | 8.75 | 7.5
35-44 | 7.8125 | 5.625 | 6.25 | 5 | 6.5625 | 6.5625 | 6.875 | 5 | 8.4375 | 4.375 | 3.125 | 8.125 | 9.0625 | 6.875
45-54 | 9.375 | 6.875 | 6.875 | 5.625 | 8.125 | 6.875 | 7.5 | 3.125 | 6.875 | 5 | 2.5 | 7.5 | 8.125 | 5.625
55-64 | 9.375 | 7.5 | 8.125 | 6.875 | 8.125 | 6.875 | 7.5 | 3.75 | 7.5 | 5 | 3.75 | 7.5 | 8.125 | 6.25
65+ | 5 | 5 | 2.5 | 7.5 | 7.5 | 10 | 7.5 | 5 | 2.5 | 5 | 2.5 | 7.5 | 7.5 | 2.5
Chart: 
| Personal level of motivation influence team | Motivated leader influences team performance | Unmotivated leader influences team performance | Degree motivation is related to team performance
18-24 | 6.4286 | 9.2857 | 7.5 | 9.2857
25-34 | 7.9167 | 9.1667 | 7.9167 | 8.3333
35-44 | 7.1875 | 8.75 | 8.4 | 8.4375
45-54 | 8.125 | 8.75 | 6.25 | 8.75
55-64 | 8.075 | 9.375 | 5 | 7.075
65+ | 5 | 5 | 5 | 5

## Slide 16
Survey Results
|Open-Ended Questions
What do you think is the most effective way to motivate your team?
Communication
Family community
Good leadership
Positive recognition
A good attitude
Be an example
Clear goals
Understand the individuals on the team

## Slide 17
Survey Results
|Open-Ended Questions
What do you think is the most effective way to motivate your team?
How does conflict affect motivation or team performance?
Communication
Family community
Good leadership
Positive recognition
A good attitude
Be an example
Clear goals
Understand the individuals on the team
If handled well, conflict can become a rallying point for a team. Conflict has a tendency to motivate me to push harder and stake my position on the high road.
“
“
Humans will not want to do something that they do not feel comfortable doing or if conflict exists between people. Team performance will be affected if conflict exists because the team will not trust each other and it will hinder communication between the two parties.

## Slide 18
Analysis 2 | Motivation
|Results
Two major drivers of motivation:
  Belief in the cause
  Respectable leader
Negative motivators
Age correlation
Trust and communication
Conflict and team performance

## Slide 19
Analysis 3 | Cash Flow
Fiscal Year | Funding (million)
FY 2014 | $18
FY 2015 | $59
FY 2016 | $91.5
FY 2017 | $53
FY 2018 | $9.5
Total | $231
Chart: 
| Other Construction Contracts | Mechanical Contract
Other Construction Contracts Mechanical Contract | 143 | 63
$63 mil
$143 mil

## Slide 20
Chart: Number of Crews
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Original Cost | 321721.5812 | 246392.5243 | 254667.514 | 333347.6414 | 235655.2809 | 735281.5529 | 1033852.2356 | 1509447.8238 | 2430778.592 | 2578948.8282 | 2511715.3033 | 3871795.4968 | 4262074.6393 | 4385800.0857 | 2639774.5993 | 2248280.2068 | 2179870.1138 | 2451723.1033 | 2133268.8326 | 2133268.8326 | 2208336.8781 | 2152472.0643 | 2152472.0643 | 2099367.2531 | 2289480.733 | 1993887.8438 | 1720307.919 | 1651260.4069 | 1452197.9336 | 1204017.9615 | 1136137.1072 | 1099502.925 | 1077157.9203 | 770082.5588 | 429675.1734 | 296217.9739 | 297778.8542 | 251872.5397 | 115402.0246 | 54829.1719
# Crews /wk | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 21 | 24 | 40 | 40 | 44 | 50 | 62 | 60 | 64 | 64 | 64 | 64 | 64 | 62 | 58 | 58 | 58 | 58 | 58 | 57 | 55 | 51 | 51 | 51 | 49 | 49 | 23 | 11 | 6 | 6 | 6 | 3 | 3
Analysis 3 | Cash Flow
Fiscal Year | Funding (million)
FY 2014 | $18
FY 2015 | $59
FY 2016 | $91.5
FY 2017 | $53
FY 2018 | $9.5
Total | $231
Chart: 
| Other Construction Contracts | Mechanical Contract
Other Construction Contracts Mechanical Contract | 143 | 63
$63 mil
$143 mil
Chart: Billing in Millions
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Manpower Cost | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 687907.0904 | 871815.1264 | 902759.4144 | 1065067.1624 | 1072803.3824 | 1112293.3344 | 1174181.3984 | 1294419.9584 | 1273790.5504 | 1311511.9584 | 1311511.9584 | 1311511.9584 | 1311511.9584 | 1311511.9584 | 1290882.7104 | 1251392.5984 | 1251392.5984 | 1251392.5984 | 1251392.5984 | 1201997.5184 | 1191311.8144 | 1163089.4864 | 1034838.4024 | 807150.4024 | 744874.4024 | 711265.068 | 686265.068 | 409044.612 | 172471.324 | 85141.552 | 85141.552 | 76075.676 | 40873.3948 | 20301.982
Equipment/Material Cost | 276564.2292 | 163902.3843 | 164585.642 | 171082.1814 | 163015.8209 | 233572.4625 | 345945.1452 | 637632.6974 | 1528019.1776 | 1513881.6658 | 1438911.9209 | 2759502.1624 | 3087893.2409 | 3091380.1273 | 1365984.0489 | 936768.2484 | 868358.1554 | 1140211.1449 | 821756.8742 | 821756.8742 | 917454.1677 | 901079.4659 | 901079.4659 | 847974.6547 | 1038088.1346 | 791890.3254 | 528996.1046 | 488170.9205 | 417359.5312 | 396867.5591 | 391262.7048 | 388237.857 | 390892.8523 | 361037.9468 | 257203.8494 | 211076.4219 | 212637.3022 | 175796.8637 | 74528.6298 | 34527.1899

## Slide 21
Chart: Billing in Millions
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Manpower Cost | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 687907.0904 | 871815.1264 | 902759.4144 | 1065067.1624 | 1072803.3824 | 1112293.3344 | 1174181.3984 | 1294419.9584 | 1273790.5504 | 1311511.9584 | 1311511.9584 | 1311511.9584 | 1311511.9584 | 1311511.9584 | 1290882.7104 | 1251392.5984 | 1251392.5984 | 1251392.5984 | 1251392.5984 | 1201997.5184 | 1191311.8144 | 1163089.4864 | 1034838.4024 | 807150.4024 | 744874.4024 | 711265.068 | 686265.068 | 409044.612 | 172471.324 | 85141.552 | 85141.552 | 76075.676 | 40873.3948 | 20301.982
Equipment/Material Cost | 276564.2292 | 163902.3843 | 164585.642 | 171082.1814 | 163015.8209 | 233572.4625 | 345945.1452 | 637632.6974 | 1528019.1776 | 1513881.6658 | 1438911.9209 | 2759502.1624 | 3087893.2409 | 3091380.1273 | 1365984.0489 | 936768.2484 | 868358.1554 | 1140211.1449 | 821756.8742 | 821756.8742 | 917454.1677 | 901079.4659 | 901079.4659 | 847974.6547 | 1038088.1346 | 791890.3254 | 528996.1046 | 488170.9205 | 417359.5312 | 396867.5591 | 391262.7048 | 388237.857 | 390892.8523 | 361037.9468 | 257203.8494 | 211076.4219 | 212637.3022 | 175796.8637 | 74528.6298 | 34527.1899
Mechanical Review of Cash Flow
Chart: Number of Crews
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Original Cost | 321721.5812 | 246392.5243 | 254667.514 | 333347.6414 | 235655.2809 | 735281.5529 | 1033852.2356 | 1509447.8238 | 2430778.592 | 2578948.8282 | 2511715.3033 | 3871795.4968 | 4262074.6393 | 4385800.0857 | 2639774.5993 | 2248280.2068 | 2179870.1138 | 2451723.1033 | 2133268.8326 | 2133268.8326 | 2208336.8781 | 2152472.0643 | 2152472.0643 | 2099367.2531 | 2289480.733 | 1993887.8438 | 1720307.919 | 1651260.4069 | 1452197.9336 | 1204017.9615 | 1136137.1072 | 1099502.925 | 1077157.9203 | 770082.5588 | 429675.1734 | 296217.9739 | 297778.8542 | 251872.5397 | 115402.0246 | 54829.1719
# Crews /wk | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 21 | 24 | 40 | 40 | 44 | 50 | 62 | 60 | 64 | 64 | 64 | 64 | 64 | 62 | 58 | 58 | 58 | 58 | 58 | 57 | 55 | 51 | 51 | 51 | 49 | 49 | 23 | 11 | 6 | 6 | 6 | 3 | 3
Chart: Billing in Millions
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Manpower Cost | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 307907.0904 | 371815.1264 | 310898.8 | 490294.052 | 898516.1952 | 1065184.2746 | 1150488.7175 | 1259463.1125 | 1422792.4911 | 1626529.6714 | 1843679.4635 | 1843679.4635 | 1860657.5618 | 1877635.6602 | 1877635.6602 | 1877635.6602 | 1843679.4635 | 1789392.0155 | 1666725.1395 | 1510569.1013 | 1455814.6188 | 1310960.9097 | 1075003.4847 | 1075003.4847 | 613736.7633 | 230153.0769 | 130932.9361 | 101473.6975 | 101473.6975 | 67113.0588 | 67113.0588 | 64184.7524 | 24981.1138 | 8573.2
Equipment/Material Cost | 276563.648 | 163901.86 | 164585.128 | 171081.54 | 163015.54 | 233571.9096 | 194193.9096 | 637632.6974 | 545031.0192 | 560025.3598 | 674579.418 | 987499.5414 | 1174166.8358 | 1489151.9437 | 2740272.9067 | 2705150.1032 | 2483718.0618 | 1948062.9553 | 1998905.205 | 1041739.47 | 1010240.2479 | 932486.8837 | 860081.985 | 844316.0224 | 1030474.7955 | 875264.8818 | 869349.728 | 790849.4109 | 492635.8179 | 496472.6187 | 460674.8452 | 398095.6666 | 387561.5697 | 372033.2428 | 181363.188 | 39055.0054 | 39055.0054 | 38668.0524 | 22553.477 | 14966.7886
Chart: Number of Crews
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Original | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 21 | 24 | 40 | 40 | 44 | 50 | 62 | 60 | 64 | 64 | 64 | 64 | 64 | 62 | 58 | 58 | 58 | 58 | 58 | 57 | 55 | 51 | 51 | 51 | 49 | 49 | 23 | 11 | 6 | 6 | 6 | 3 | 3
Mech Review | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 10 | 15 | 22 | 28 | 41 | 43 | 54 | 60 | 72 | 80 | 80 | 82 | 82 | 82 | 82 | 82 | 80 | 72 | 64 | 62 | 56 | 46 | 46 | 28 | 15 | 12 | 9 | 9 | 6 | 6 | 6 | 3 | 2
|Mechanical
Review
|Original

## Slide 22
Mechanical Review
Man-loaded Schedule
Legend

## Slide 23
Modified Man-loaded Schedule
Legend

## Slide 24
Modified Man-loaded Schedule
Chart: Manpower Cost
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Mech Review | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 307907.0904 | 371815.1264 | 310898.8 | 490294.052 | 898516.1952 | 1065184.2746 | 1150488.7175 | 1259463.1125 | 1422792.4911 | 1626529.6714 | 1843679.4635 | 1843679.4635 | 1860657.5618 | 1877635.6602 | 1877635.6602 | 1877635.6602 | 1843679.4635 | 1789392.0155 | 1666725.1395 | 1510569.1013 | 1455814.6188 | 1310960.9097 | 1075003.4847 | 1075003.4847 | 613736.7633 | 230153.0769 | 130932.9361 | 101473.6975 | 101473.6975 | 67113.0588 | 67113.0588 | 64184.7524 | 24981.1138 | 8573.2
Modified | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 307907.0904 | 371815.1264 | 310898.8 | 490294.052 | 898516.1952 | 1065184.2746 | 1657727.1001 | 1487118.2143 | 1507682.9829 | 1507682.9829 | 1507682.9829 | 1507682.9829 | 1490704.8846 | 1507682.9829 | 1507682.9829 | 1623070.3517 | 1589114.1549 | 1568782.9036 | 1738457.7204 | 1622836.8344 | 1622836.8344 | 1487448.1992 | 1383856.2412 | 1322756.3205 | 1007773.1792 | 375602.533 | 246898.9441 | 172955.6788 | 101473.6975 | 67113.0588 | 67113.0588 | 64184.7524 | 24981.1138 | 8573.2
Fiscal Year | Funding | Mechanical Review Billing | Modified Billing | Difference
FY 2014 | $18,000,000 | $321,700 | $321,700 | --
FY 2015 | $59,000,000 | $10,910,600 | $11,463,500 | $552,900
FY 2016 | $91,500,000 | $39,874,100 | $37,377,100 | ($2,497,000)
FY 2017 | $53,000,000 | $13,141,800 | $15,086,200 | $1,944,500
FY 2018 | $9,500,000 | $173,900 | $174,000 | $100
Chart: Manpower Curve
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Mech Review | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 10 | 15 | 22 | 28 | 41 | 43 | 54 | 60 | 72 | 80 | 80 | 82 | 82 | 82 | 82 | 82 | 80 | 72 | 64 | 62 | 56 | 46 | 46 | 28 | 15 | 12 | 9 | 9 | 6 | 6 | 6 | 3 | 2
Modified | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 10 | 15 | 22 | 28 | 41 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 70 | 70 | 70 | 75 | 70 | 70 | 65 | 60 | 57 | 48 | 20 | 20 | 9 | 9 | 6 | 6 | 6 | 3 | 2
Mech Review | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 10 | 15 | 22 | 28 | 41 | 43 | 54 | 60 | 72 | 80 | 80 | 82 | 82 | 82 | 82 | 82 | 80 | 72 | 64 | 62 | 56 | 46 | 46 | 28 | 15 | 12 | 9 | 9 | 6 | 6 | 6 | 3 | 2
Modified | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 10 | 15 | 22 | 28 | 41 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 70 | 70 | 70 | 75 | 70 | 70 | 65 | 60 | 57 | 48 | 20 | 20 | 9 | 9 | 6 | 6 | 6 | 3 | 2

## Slide 25
Analysis 3 | Cash Flow
Chart: Modified Total Cash Flow
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Manpower Cost | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 307907.0904 | 371815.1264 | 310898.8 | 490294.052 | 898516.1952 | 1065184.2746 | 1657727.1001 | 1487118.2143 | 1507682.9829 | 1507682.9829 | 1507682.9829 | 1507682.9829 | 1490704.8846 | 1507682.9829 | 1507682.9829 | 1623070.3517 | 1589114.1549 | 1568782.9036 | 1738457.7204 | 1622836.8344 | 1622836.8344 | 1487448.1992 | 1383856.2412 | 1322756.3205 | 1007773.1792 | 375602.533 | 246898.9441 | 172955.6788 | 101473.6975 | 67113.0588 | 67113.0588 | 64184.7524 | 24981.1138 | 8573.2
Equipment/Material Cost | 276563.648 | 163901.86 | 164585.128 | 171081.54 | 163015.54 | 233571.9096 | 194193.9096 | 374619.8736 | 545031.0192 | 560025.3598 | 674579.418 | 987499.5414 | 1219818.4064 | 1509640.955 | 2750634.271 | 2691733.122 | 2446808.5983 | 1911153.4918 | 1958026.081 | 1000866.9489 | 969367.7268 | 904421.8678 | 832003.7635 | 820199.69 | 1038894.7318 | 888618.5897 | 888618.5897 | 810969.5131 | 527480.2266 | 524397.0168 | 505862.4102 | 417179.1697 | 403176.2819 | 381660.1894 | 181426.7028 | 39096.9592 | 39096.9592 | 38708.2095 | 22569.0827 | 14972.7852

## Slide 26
Analysis 3 | Cash Flow
Chart: Modified Total Cash Flow
| 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979
Manpower Cost | 45157.352 | 82490.14 | 90081.872 | 162265.46 | 72639.46 | 501709.0904 | 307907.0904 | 371815.1264 | 310898.8 | 490294.052 | 898516.1952 | 1065184.2746 | 1657727.1001 | 1487118.2143 | 1507682.9829 | 1507682.9829 | 1507682.9829 | 1507682.9829 | 1490704.8846 | 1507682.9829 | 1507682.9829 | 1623070.3517 | 1589114.1549 | 1568782.9036 | 1738457.7204 | 1622836.8344 | 1622836.8344 | 1487448.1992 | 1383856.2412 | 1322756.3205 | 1007773.1792 | 375602.533 | 246898.9441 | 172955.6788 | 101473.6975 | 67113.0588 | 67113.0588 | 64184.7524 | 24981.1138 | 8573.2
Equipment/Material Cost | 276563.648 | 163901.86 | 164585.128 | 171081.54 | 163015.54 | 233571.9096 | 194193.9096 | 374619.8736 | 545031.0192 | 560025.3598 | 674579.418 | 987499.5414 | 1219818.4064 | 1509640.955 | 2750634.271 | 2691733.122 | 2446808.5983 | 1911153.4918 | 1958026.081 | 1000866.9489 | 969367.7268 | 904421.8678 | 832003.7635 | 820199.69 | 1038894.7318 | 888618.5897 | 888618.5897 | 810969.5131 | 527480.2266 | 524397.0168 | 505862.4102 | 417179.1697 | 403176.2819 | 381660.1894 | 181426.7028 | 39096.9592 | 39096.9592 | 38708.2095 | 22569.0827 | 14972.7852
|Recommendations
Resource Leveling Recommended ✔

## Slide 27
Analysis 1 Shoring System
Sheet Piles Recommended ✔

## Slide 28
Analysis 1 Shoring System
Analysis 2
Motivation
Sheet Piles Recommended ✔
Two major drivers of motivation:
  Belief in the cause
  Respectable leader
Negative motivators
Age correlation
Trust and communication
Conflict and team performance

## Slide 29
Analysis 1 Shoring System
Analysis 2
Motivation
Analysis 3
Cash Flow
Sheet Piles Recommended ✔
Resource Leveling Recommended ✔
Two major drivers of motivation:
  Belief in the cause
  Respectable leader
Negative motivators
Age correlation
Trust and communication
Conflict and team performance

## Slide 30
Dr. Somayeh Asadi
Dr. Rob Leicht
Kevin Parfitt
Walt Schneider
Analysis 1 Shoring System
Analysis 2
Motivation
Analysis 3
Cash Flow
Sheet Piles Recommended ✔
Resource Leveling Recommended ✔
Two major drivers of motivation:
  Belief in the cause
  Respectable leader
Negative motivators
Age correlation
Trust and communication
Conflict and team performance
|Acknowledgements
Academic
Industry
Special Thanks
HSFIII Team
Roger Stadler
Chuck Briney
Josh Kraus
Bill Gamble
Chris Brooks
Other Industry Leaders
Jason McFadden
Family and Friends
Jesus Christ

## Slide 31
Questions?

## Slide 32
Appendix

## Slide 33
Appendix

## Slide 34
Brick
Curtain Wall
Granite
Metal Panel
Punch Windows
Precast
100 ft
200 ft
246 ft
Architectural Breadth

## Slide 35
|Original
|Modified
Architectural Breadth

## Slide 36
|Material Selection
|Recommendations
Material Restrictions
60” width
Limited to certain colors
R-Value
Precast: 1.22
Metal Panel: 2.63
Cost/SF
$103
$44
Omega-Lite®
Better R-Value
Cheaper Cost/SF
Similar Panel Layout
Metal Panel
Recommended ✔
Architectural Breadth

## Slide 37
Alternative Systems
|Sheet Piles
|Slurry Wall

## Slide 38
Comparison Matrix
|Availability
|Constructability
45.8 miles
18.3 miles
31.0 miles
http://www.directindustry.com/prod/international-construction-equipment-bv/pile-driving-vibrator-hydraulic-64206-431915.html
http://www.lowes.com/pd_46905-432-TC248T225N_0__?productId=3185207
http://www.omranista.com/eng/tech5.php
Sheet Piles
Pile and Lagging
Slurry Wall

## Slide 39
Literature Review
|Maslow’s Hierarchy of Needs
|5 Dysfunction of a Team
Self-Actualization
Esteem
Physiological
Social
Safety
Inattention to results
Avoidance of accountability
Absence of Trust
Lack of Commitment
Fear of Conflict

## Slide 40
Survey Results
Chart: 
| Not at all | Very little | Somewhat | Significantly | Very significantly
To what degree do you think a motivated leader influences your team performance? | 0 | 0 | 1 | 11 | 18
Chart: 
| Not at all | Very little | Somewhat | Significantly | Very significantly
To what degree do you think motivation is directly related to team performance? | 0 | 0 | 4 | 11 | 14
Chart: 
| Not at all | Very little | Somewhat | Significantly | Very significantly
To what degree do you think your level of motivation influences your team? | 0 | 1 | 5 | 18 | 5
Chart: 
| Not at all | Very little | Somewhat | Significantly | Very significantly
To what degree do you think an unmotivated leader would influence your team performance? | 2 | 4 | 1 | 10 | 12
|Team Performance
To what degree do you think your level of motivation influences your team?
To what degree do you think an unmotivated leader would influence your team performance?
To what degree do you think a motivated leader influences your team performance?
To what degree do you think motivation is directly related to team performance?

## Slide 41
Original Man-loaded Schedule
Legend